## Sheet1
| Error |  | Desktop |  | Fixed, InProgress, Not Fixed
| Missing Feature |  | Mobile |  | Not Started, Ready for Testing
Sr# | Issue Type | Issue | Platform | Date Reported | Status | Client Comments | Developer Comments
7 | Address verification | Api from Fedex | Desktop and mobile | 2015-08-19 | see comment | It works can you have it show in an order page to verify address like gazelle. plz.
21 | Reminders and automatic email generator | we need 5 automatic email to generate. 1) when receive package 2) when adjusted payment needed 3) item is paid 4) reminder email every 7 days for 1 month for the person to send their item. After the 1 month the email doesn't send anymore..5) return item I sent you an example Of how gazelle reminder look like if you can redesign the way it look and also redesign the way the label emai | Desktop and mobile | 2015-08-19 | Waiting for text | Ask me for pictures of how they look like
29 | backend: Newsletter | Need to add the way to send people email | Desktop and mobile | 2015-08-19 | Leave this for now
31 | Message back end and front end dashboard | I want it to show the number 1 sign if there is a message in red, so I know there is a message. Because no one will know if there is a new message | Desktop and mobile | 2015-08-19 | Leave this for now
33 | add the check format quickbook format, when someone select check for it to be able to print when you say pay order | . | Desktop and mobile | 2015-08-19 | Phase 2
45 | Blog | need to add a blog | Desktop and mobile | 2015-08-20 | Phase 2
61 | Google | Can you please add the google. you forgot to put it plz: google followers | Desktop and mobile | 2015-08-24 | Leave this for now
101 | When you make an order | No email is sent to confirm the order | Desktop and mobile | 2015-08-27 | not fixed: see comment | Gmail work. but hotmail need to work as well. plz find a solution | are you trying on hotmail aacount please check on gmail
130 | Live Chat | Live Person | Desktop and mobile | 2015-09-03 | Not started
131 | what if someone want to opt out in newsletter |  |  | 2015-09-03
133 | Remove the recycle link where you put it | Put it in footer. |  | 2015-09-03 | see comment | Rename to : Recycle
134 | Put Paypal | Paypal connection in the back end for it to work |  | 2015-09-03 | see client: see comment | in back end. when someone choose paypal and i release payment to customers | Where to put paypal?
135 | Site Map | Need to finish the site map and add rest of changes and connect the links |  | 2015-09-03 | Ready for testing
136 | Express check out deosnt verify email. when it ask to reenter email address |  |  | 2015-09-03 | Ready for testing
137 | google analytics |  |  | 2015-09-03 | See developer comments |  | Can you send google analytics code
138 | use a permanent (HTTP 301) redirect |  |  | 2015-09-03
139 | 404 HTTP |  |  | 2015-09-03 | Ready for testting
140 | GZIP encoding | This is very good because it reduces the loading time of a web page. |  | 2015-09-03 | Ready for testting
141 | index.php or .php | Avoid use of file extensions |  | 2015-09-03 | Ready for testting
142 | Meta tags | i dont think we have Meta tags |  | 2015-09-03 | See developer comment |  | We have added the meta tags
143 | Page titles |  |  | 2015-09-03
144 | put security in mobile as well | ssl | Mobile | 2015-09-03
145 | Please add a space in the back end for order: | Add: "Track Payment" This is when i sent a check to i can put the usps tracking number. Have it appear in front as well please. for paypal have it display in front the paypal transaction number. | Desktop and mobile | 2015-09-03 | Ready for testing
146 | Align the track order when someone put their stp and email | Align them well | Mobile | 2015-09-03
147 | account activation: Backend | Make the connection for administrator to be able to activate the account in back end for the person. the activation appear but doesnt work | Desktop and mobile | 2015-09-03 | Ready for testing
148 | Hot Item picture BOX | Need to be formatted just like the other picture box. no matter how much i reduce size the picture for the iphone 6 it appear the same in the Hot item. plz adjust it so it can be just like the rest of the box. | Desktop and mobile | 2015-09-07 | See developer comment |  | We checked images are of diiferent sizes we mentioned before use images of resolution 522x230 in that case images will look good in boxes
149 | I added picture in the cpanel. make the connection. Most of them were not right. So now you can make connection with proper image. | . | Desktop and mobile | 2015-09-07
150 | Some box that contain the picture doesnt have the same format as the rest of the box . cuz picture turn out to be wieird in them. while other picture have the same exact size but looks good .example : Macbook air- iphone in the hot menu- galaxy s6 in the hot menu | . |  |  | See developer comments |  | We checked images are of diiferent sizes we mentioned before use images of resolution 522x230 in that case images will look good in boxes

## Error Screenshot
Sr# | Issue Type | Issue | Platform | Date Reported | Status | Client Comments | Developer Comments
35 | All reminders |  | Desktop and mobile | 2015-09-03
36 | Recycle | Put this text instead. and make them clickable where it should be you will see it: example: e-stewards. | Desktop and mobile | 2015-09-03 | Ready for testing
37 | Error i get while on website | admin product | Desktop and mobile | 2015-09-03 | Ready for testing |  | This is the correct link https://www.stopoint.com/admin/product.php?catid=all
38 | Whie on admin product |  | Desktop and mobile | 2015-09-03 | Ready for testing
39 | While browsing on website |  | Desktop | 2015-09-06 | Ready for testing
40 | Search bar. : i add pic in folder | see pic: make it smaller it keep on jumping to other product |  | 2015-09-07 | Ready for testing
41 | Search bar. :see pic | I am viewing this on safari

## Completed
Sr# | Issue Type | Issue | Platform | Date Reported | Status | Client Comments | Developer Comments
1 | Express Checkout | Only Email Address | Desktop and mobile | 2015-08-19 | fixed
2 | Popular Search | The word popular search is too big. | Desktop | 2015-08-19 | fixed |  | We have linked the last column also please check, for shrinking it would not look good in current design as page is full width
6 | Orders in back end | This is the way I want the order to look like: | Desktop and mobile | 2015-08-19 | fixed |  | .
|  | 1) Tracking Number |  |  |  |  | .
2) Product Code
3) Name
4) Order Number
5) Generation
6) Description
7) Condition
8) Amount
9) Adjusted Price
10) Order Status
11) Date Created
8 | payment option | only 1 is display: sometimes check is display, sometimes paypal | Desktop and mobile | 2015-08-19 | fixed |  | It depends on user selection if user selected Cheque it would show Cheque otherwise paypal if user didn't selected any payment method it would show both
9 | What shaped is it in | You do not put the description in the proper place. Flawless description.and good | Desktop and mobile | 2015-08-19 | fixed | I am talking about the condition when completing an order: fair-flawless. the word in the bottom of them that say; Your phone is in this condition if the following are true:
10 | Macbook Pro | When you go to : Macbook Pro 13"- 2.6 GHZ I5- | Desktop and mobile | 2015-08-19 | Fixed | There is 2 of 256GB display
11 | Footer= All right reserve | ©2015 Stopoint, Inc. All Rights Reserved, Patents Pending.Stopoint is not affiliated with the manufacturers of the items available for trade-in. Stopoint and the Stopoint logo are trademarks of Stopoint, Inc., registered in the U.S. All other trademarks, logos and brands are the property of their respective owners. | Desktop and mobile | 2015-08-19 | Fixed
12 | when you go to website | It appear a red color while loading | Mobile | 2015-08-19 | Fixed
13 | Login | It should pop up to log in just like you showed us in design | Desktop | 2015-08-19 | fixed |  | Login pop up wont look good in responsive mobile view so we used separate page
15 | The green steps | select brand-family-specification: are not needed | Mobile | 2015-08-19 | fixed
16 | Products | All pictures need fixing , when you flip phone they look so bad | Mobile | 2015-08-19 | fixed |  | Please check for mobile now
17 | Select Model in making an order | Need fixing they are not align right | Mobile | 2015-08-19 | fixed
18 | What shaped is it in | is very bad arrangement in phone not align | Mobile | 2015-08-19 | fixed | the green line is not align and its not very align. when you do it for iphone it looks okay but for macbooks it doesnt look good
25 | In dashboard | Fedex# should be clickable to direct you to fedex | Desktop and mobile | 2015-08-19 | fixed | I will show u example. ask me when you are ready
25 | Trace Your orders | People should be able to download their label from there as well. | Desktop and mobile | 2015-08-19 | fixed | put generate label button
26 | testimonials | how can people add testimonials I don’t see it- Also We need to reply in the testimonial, some people choose to ask their questions there. | Desktop and mobile | 2015-08-19 | fixed | it is good, but can u make a different icon so people know what it is plz- And also it gives a boolean error
27 | on orders | make it display the condition exactly how it is in front end. if it is flawless it should also display flawless in back end not "like new" | Mobile | 2015-08-19 | fixed | it does not populate the drop down | We have added it in My Account My orders section In front of each order there is a link
28 | While checking out | If someone forget to add state-zipcode-city-phone: it still let it completed. | Desktop and mobile | 2015-08-19 | fixed
32 | View Orders | Only person in view order can delete | Desktop and mobile | 2015-08-19 | fixed | only the person in View order can delete the rest department cannot
35 | on order: adjusted Orders | on adjusted order: 2 status: release payment and return order | Desktop and mobile | 2015-08-19 | Fixed
36 | Help section | need alignment | Mobile | 2015-08-19 | Fixed
37 | Track your order | writing on the pop up is too big | Mobile | 2015-08-19 | fixed
38 | Hot Items | To be able to click on the picture as well | Desktop | 2015-08-19 | fixed
40 | Adjusted price | If you click on return order while in the adjusted price.it still ask you to put the adjusted price | Desktop and mobile | 2015-08-20 | fixed | when you select release payment if the person dont put the price adjustment, it should give a warning. if it is a return no warning | Select Carrier is according to the design.
41 | Apple watch section | has a code error | Desktop and mobile | 2015-08-20 | Fixed
51 | error | http://unidevphp.com/stopoint/Tv.php?model=995 | Desktop and mobile | 2015-08-24 | fixed
52 | Specification |  | Desktop and mobile | 2015-08-24 | fixed | need to do for the rest> check gazelle. ipad-ipod-surface- samsung phone and tablet- check gazelle.
53 | Dashboard | Under dashboard,it force the user to put their paypal email when the user doesnt even want to select paypal as payment method. check into that plz | Desktop and mobile | 2015-08-24 | fixed
54 | select screen and try select processor | http://unidevphp.com/stopoint/computers.php?specification=MacBook%20Pro | Desktop and mobile | 2015-08-24 | fixed | not align
55 | for phone- tablet-ipod-ipad-tv | for the condition: the flawless is not display in the right place. the description that describe what flawless is | Desktop and mobile | 2015-08-24 | fixed
14 | The writing on top : Trade in | Make it take 2 lines | Mobile | 2015-08-19 | fixed | make the writing a little bigger. it is way too small to read
19 | Email verification | if the verification doesn’t send and when the person try the email it says error. It should give you option to say email need verification resend verification process | Desktop and mobile | 2015-08-19 | fixed | it appears, however, the email does not send to the person
22 | Transaction completed | Need alignment | Mobile | 2015-08-19 | fixed | the line that say transaction completed there is an arrow and it is not align | Please check we checked on mobile it looks good
42 | Shipping Address | Need Full name of person: because for a guess user creating a label. it will appear in the label as guess user for name. | Desktop and mobile | 2015-08-20 | fixed | the label should show the name the person provide and address. the guess user should be for just account not for label. it should be separate | We have made th full name field required on checkout page so user needs to put his full name on checkout. Now no Guest User would passed to the lable
62 | I sent picture | i sent picture in email | Desktop and mobile | 2015-08-24 | fixed
63 | I sent picture | i sent picture in email | Desktop and mobile | 2015-08-24 | fixed
60 | Popular Search | in the popular search. You spell : MacBook and Google Tablet wrong. thanks | Desktop and mobile | 2015-08-24 | fixed
65 | Need alignment | http://unidevphp.com/stopoint/testimonials.php | Mobile | 2015-08-26 | fixed
77 | SIZE adjustment | in email i have attached pic | Mobile | 2015-08-26 | fixed |  | We have increase the size please check, the image you send us have different font style we increase the size according to current font style
49 | Export orders | I want to be able to export everything: example like it is in products- and add the rest which is the rest of the information; NAME-ADDRESS-EMAIL-PHONE-PAYMENT METHOD. WHAT EVER THE PERSON PROVIDE |  | 2015-08-21 | fixed | almost completed. also i want the description to be exported as well
56 | Check out | Payment and shipping details is not align | Mobile | 2015-08-24 | fixed
70 | Apple TV | Generation Need alignment | Mobile | 2015-08-26 | fixed
73 | Need alignment | http://unidevphp.com/stopoint/gadgets.php?model=983 | Mobile | 2015-08-26 | fixed | get paid is not align. and when you click on flawless doesnt work
74 | Need alignment | http://unidevphp.com/stopoint/tablets.php?model=1128 | Mobile | 2015-08-26 | fixed | get paid is not align. and when you click on flawless doesnt work
75 | Need alignment | http://unidevphp.com/stopoint/cellphone.php?model=612 | Mobile | 2015-08-26 | fixed | get paid is not align. and when you click on flawless doesnt work
76 | condition be in 1 line | http://unidevphp.com/stopoint/cellphone.php?model=715 | Mobile | 2015-08-26 | fixed | get paid is not align. and when you click on flawless doesnt work
82 | i sent picture in email | Social media look like that | Desktop and mobile | 2015-08-26 | fixed
83 | Cart | The item that is in the shopping cart. you cannot click on it inside the mobile. it is not align | Mobile | 2015-08-26 | fixed
84 | condition: fair-good-flawless: are not align | http://unidevphp.com/stopoint/computers.php?computer=798 | Mobile | 2015-08-26 | fixed
86 | When you trying to complete an order when you click on Flawless. it doesnt work. it stays on good |  | Desktop and mobile | 2015-08-26 | fixed
87 | when you click on flawless it doesnt work | That apply to all the products | Desktop and mobile | 2015-08-26 | fixed
88 | Search bar-Product typing | when you type MB463LL/A. The way the result appear is really off and that apply for many other product. or when you just type "M" they appear different than in my excel file | Desktop and mobile | 2015-08-26 | fixed
90 | Views order | When you try to delete something. after you press deleted everything disappear. and also can you put the option to delete many order at once | Desktop and mobile | 2015-08-26 | fixed
80 | Shopping | Can you change design of shopping cart to something more classy | Desktop and mobile | 2015-08-26 | fixed | the only ugy looking thing in website lol
47 | Sub-Admin | Permission is not working when i create an account | Desktop and mobile | 2015-08-21 | fixed | i add a new sub-admin even when i give specific permission that person has access to all
3 | Social Media: Facebook and twitter-google plus in the bottom | I want to see facebook likes only and twitter followers only. | Desktop and mobile | 2015-08-19 | fixed | The facebook likes that i have already i want them to display as well
5 | Cart | need to say 1 item is in the cart | Desktop | 2015-08-19 | fixed | have it display 1 plz. otherwise everythign is fix | .
89 | I sent image | alignment | Desktop and mobile | 2015-08-26 | fixed
59 | Email that is sent for when someone create an order to tell the shipping label | It is a complete copy of gazelle. can you make it ours a little redesign. and also the way it is display: Stopoint - and the second line should appear: Your Stopoint Shipping Information | Desktop and mobile | 2015-08-24 | fixed | the way it appear say : info@stopoint.com and stopoint order. Keep the box borders for the product plz | We have made some changes
66 | Need alignment | http://unidevphp.com/stopoint/about.php | Mobile | 2015-08-26 | fixed | The circle display 24/7 is not align in the center
93 | When you click on ipad should it take u to another page just like the other one. it appears all the way in the bottom a little confusing. | http://unidevphp.com/stopoint/tablets.php?generation=1st%20Gen | Desktop and mobile | 2015-08-26 | fixed |  | We have made changes please check now it would be not confusing now
95 | Flawless condition is not align with the rest | http://unidevphp.com/stopoint/computers.php?computer=915 | Mobile | 2015-08-27 | fixed
96 | Forget Your password | when you click on it: the text is way too big | Mobile | 2015-08-27 | fixed
48 | I sent you email | When somoene upload a picture on their profile; the size should be limit to 213 by 213. because if someone upload a picture and the size is big. it looks so bad | Desktop and mobile | 2015-08-21 | fixed | almost there but pic need to be align. 213 by 213 is the perfect size.
57 | for samsung-google | http://unidevphp.com/stopoint/tablets.php | Desktop and mobile | 2015-08-24 | not fixed | it used to work fine. well it has to work because are we sayign all people with hotmail are excluded | We are trying to find the solution Hitmail is not accepting mails from our server
58 | Guess | When you create an order with a guess account : email does not send with the generated password on email | Desktop and mobile | 2015-08-24 | fixed |  | Its working fine for yahoo and gmail for hotmail it's not working some mail spamming issue please confirm for other mail provider and check for gmail and yahoo
69 | None of the verizon work- and you wrote verizon wrong | http://unidevphp.com/stopoint/cellphone.php?carrier=Verizon | Desktop and mobile | 2015-08-26 | fixed | click on the link you will see what i mean | User can not access the carrier without completing 1st 2 steps that's why we showed error on that page in red
103 | email activation | When you click to activate email: it gives an unkown message | Desktop and mobile | 2015-08-27 | fixed
4 | Search Bar | now make it work when you click on the result | Desktop and mobile | 2015-08-19 | fixed | Try typing the order number: example - MD101LL/A. and when you click on somehting it doesnt work
22 | Search bar | Need alignment | Mobile | 2015-08-19 | fixed | on the iphone try with the simulator i sent u. the search bar still not align.
102 | For tablet : | After you click carrier: it should take you to another page just like every other ones. | Desktop and mobile | 2015-08-27 | fixed
105 | Testimonial | bad programming: If You delete order, why should testimonials be affected. Testimonials should have nothing to do with someone removing an order. as long as someone sent a testimonals. it should stay. | Desktop and mobile | 2015-08-27 | fixed
107 | I sent email | Search bar | Mobile | 2015-08-28 | fixed
110 | Product | can we have something to View all Products. Just like we have view all orders | Desktop and mobile | 2015-08-28 | fixed
111 | all Records | when you select to view more than 50 products it doesnt work | Desktop and mobile | 2015-08-28 | fixed
112 | after i press activate | I try to log in and it still not letting me log in: guess account. | Desktop and mobile | 2015-08-28 | fixed
113 | the text. it say ipad mini 316.. seperate them plz | http://unidevphp.com/stopoint/tablets.php?generation=3rd%20Gen | Desktop and mobile | 2015-08-28 | fixed
114 | Mac Mini | When you try to make order with mac mini doesnt work | Desktop and mobile | 2015-08-28 | fixed
64 | Hot Items | Can you put better quality pictures. those pictures are not good. take them from amazon. | Desktop and mobile | 2015-08-24 | fixed
79 | inside search bar | Have this display: "Search by Brand, Model and/or Specifications" | Mobile | 2015-08-26 | fixed | almost. fixed. word is still need a little fix
81 | i sent picture in email | If you have it display like that it will be exceptional and very beautiful( mobile only) | Mobile | 2015-08-26 | fixed | Then dont put it there. remove the entire top and do the rest of the picture i sent u | We told you its not possible its list menu we can not put the top inside menu, we can't remove entrire top
116 | i sent picture in email | in iphone 6 not align | Mobile | 2015-08-28 | fixed
117 | I sent image | Hot items | Desktop and mobile | 2015-08-28 | fixed
97 | I sent email with 3 pictures of what i describe | people do not need to view all the 3 testimonials, have it display 1 and option to click to view the rest.the top does not need to have the bar that say welcome to stopoint. The footer in the bottom just have the way i have it on stopoint.com to display: Help- Terms of service- live chat….. | Mobile | 2015-08-27 | fixed | when you click on terms of services you can see the rest of the About us. mobile is too pack. because it is too pack it looks ugly. with those changes. it iwll be nice
120 | Display picture in front end | I need to be able to change the display picture in front end. when i add new products. and to add a picture for each product. | Desktop and mobile | 2015-08-28 | fixed |  | We added functionality add admin panel to upload product image, on front end user can see the added product image on what shape is it in section after selecting product fro order
2 | i sent you image | I check every singly category on my iphone this is how they look | Mobile | 2015-08-28 | fixed
124 | Put track order in the bar as well | in the drop down menu | Mobile | 2015-08-31 | fixed
125 | The picture i upload for products: When i am making an order the picture of product should display when you reach model | http://unidevphp.com/stopoint/computers.php?model=1%20TB&process=3.2%20GHz%20Core%20i5&screen=27 | Desktop and mobile | 2015-08-31 | fixed
126 | Align the "Help. Terms of service , Live chat in the bottom. | . | Mobile | 2015-08-31 | fixed
127 | search bar | when you click on search bar it drop a white thing. dont let that happen. only the products appear when you start typing. and also when you start typing A1278. nothing appear can you fix that as well. this is the model number | Desktop and mobile | 2015-08-31 | fixed | it is fixed for the mobile not fix it for desktop
128 | Remove the track order under "My Stopoint" and put it on top of it | . | Mobile | 2015-08-31 | fixed
23 | Fedex Label | Should be in PDF | Desktop and mobile | 2015-08-19 | fixed | is there a way to not show the html at all and only show the pdf. | We have added download pdf link to the packing slip page please check http://unidevphp.com/stopoint/packingslip.php?track=STP40438611225
34 | Admin: view user | Give me a way to suspend someone email without having to just delete the account since they can just recreate a new email | Desktop and mobile | 2015-08-19 | fixed
88 | Search bar-Product typing | Type : M and start scrolling down you will see they are not fix | Desktop and mobile | 2015-08-27 | fixed | When you type: MC239-MC238-MC936 they show those weird letters
115 | Samsung Phone | Phone Specification- should display : The product description inside the Text. | Desktop and mobile | 2015-08-28 | fixed | people should be able to see the whole description of what they are goign to trade when the reach: "Specification"
1 | i sent you image | Mobile view | Mobile | 2015-08-28 | fixed | Almost done after you remove the bar on top.
3 | i sent you image | Remove those and align plz. instructions is as follow | Mobile | 2015-08-31 | fixed
4 | i sent you image |  | Mobile | 2015-08-31 | fixed
5 | I sent you image |  | Mobile | 2015-08-31 | fixed
6 | I sent you image |  | Mobile | 2015-08-31 | fixed
7 | I sent you image |  | Mobile | 2015-08-31 | fixed
8 | I sent you image |  | Mobile | 2015-08-31 | fixed
9 | I sent you image |  | Desktop | 2015-08-31 | fixed
11 | I sent you image | shrink everywhere | Mobile | 2015-08-31 | fixed
19 | I added pic | Alignment problem | Desktop/Desktop | 2015-08-31 | fixed
20 | I added pic | Alignment problem- Text | Desktop/Desktop | 2015-08-31 | fixed
21 | I added pic | Alignment problem- Text- When i add pic | Desktop/Desktop | 2015-08-31 | fixed
22 | I added pic | Alignment problem- Text- When i add pic | Desktop/Desktop | 2015-08-31 | fixed
24 | I added pic | Alignment problem | Desktop/Desktop | 2015-08-31 | fixed
18 | I added pic | Alignment problem | Desktop/Desktop | 2015-08-31 | fixed
123 | Cart | After someone complete the order in the cart. why is it still showing and display as if the order did not complete. The cart should display after the person complete the order that is on the cart. | Desktop and mobile | 2015-08-28 | fixed
124 | Ipad-Samsung- Google-Microsof : carrier | CAn you please put all the carriers | Desktop and mobile | 2015-08-28 | fixed
43 | Address in front end | The state doesnt display | Desktop and mobile | 2015-08-20 | fixed | The state is not display in safari browser. i tested with other browser , it shows | We checked it is working fine On Payment conformation page we used Short form of State, can you please tell us where you cannot see state please send screenshot
109 | Tablet- no need for generation for the following | Can you not Show Generation for- Samsung- Google-Microsoft-- Exception : ipad | Desktop and mobile | 2015-08-28 | fixed | also after you choose carrier, the result that appear should appear with the full product description.
23 | I added pic | For Phone-tablet-watches-apple tv-ipod- When you get to specification it should display the picture that i put and the text coming from Product description. For Macbook When you get to Select Model it should display the picture that i put and the text coming from Product description | Desktop/Desktop | 2015-08-31 | fixed
27 | I added pic | shopping cart not align | mobile |  | fixed
12 | See in folder | Have the cart display there instead. | Mobile | 2015-08-31 | FIXED | Almost done.Have it display the letter 1 when something is in the cart
122 | Return | When the person in return section return the item: it is suppose to generate a return label for the person: which should be under status in return: Generate return label. | Desktop and mobile | 2015-08-28 | fixed | It should be easy to implement you already have the code provided for you and i need to be able to print it to put on the box to send to the person. Address will be other way around. Person should be able to see it in front : return tracking. that's all
123 | Return label | Have the return id appear in front for fedex for the person to track their order.( In front end) | Desktop and mobile | 2015-09-02 | fixed |  | Now return fedex Id would appear in Fedex column for return orders
124 | For Product | for the search bar: when i type the order number make it work plz | Desktop and mobile | 2015-09-02 | fixed
125 | In the search bar | If you type: MGEQ2LL/A : and then press enter : it bring you to another page when you click on that it gives error. can you fix that | Desktop and mobile | 2015-09-02 | fixed
126 | for tablet | For tablet When you get to specification it should display text coming from Product description. you fix for the other ones except table: such as google-samsung- | Desktop/Desktop | 2015-09-02 | fixed
13 | For PDF LAbel | See image PDF in folder: Plz have it close to that. look the label in the last page how it is well fit | Desktop/Desktop | 2015-08-31 | fixed | Make the label in the last page fit a little bit more a little more shrink. when u print it . it looks too big a little bit
14 | Inside the label | There is a number it is suppose to be the number the person provide. just remove it completely. | Desktop/Desktop | 2015-08-31 | fixed | then make the person contact number appear instead of fake number | We can not remove this as Contact number is required for Fedex Label
16 | I added pic | Alignment problem | Desktop/Desktop | 2015-08-31 | fixed
17 | I added pic | Alignment problem | Desktop/Desktop | 2015-08-31 | fixed
24 | in the pdf there is also a bar code scan | STP977477747: has a bar code to scan | Desktop and mobile | 2015-08-19 | fixed | Perfect i liek it. but i try to scan it it doesnt work. i use iphone app which i usually scan with | We used the same barcode generator which is currently working on your live website stopoint.com. Only difference is Our have Letters STP infront of code
15 | I added 2 picture in folder name: SR#15 | when you shrink browser why does it affect the phone on the top :try to shrink your desktop with this website: fiverr.com .... the picture of the person stay same and is not affected or look messy with the search bar | Desktop | 2015-08-31 | fixed | Writing still jump on the apple watch"FreeShipping" still jump on top of apple watch
26 | I added pic | Add picture to their right products. | Desktop/Desktop | 2015-09-02 | fixed | Show me after how to put the image in the stuff in case i add a new product | We put images in folder admin/product_images in public_html on server you can chnage images there please upload png images
28 | I added pic | When i test with Edge browser | Desktop | 2015-09-02 | fixed | Remove the small triangle from design
29 | I added pic | Alignment | Desktop/Desktop | 2015-09-03 | fixed
30 | I added pic | Alignment | Desktop/Desktop | 2015-09-03 | fixed
31 | I added pic | Alignment | Desktop/Desktop | 2015-09-03 | fixed
32 | I added pic | Alignment |  |  | fixed
33 | New Sheet Template with Image include as you told me | I Put in folder errors: instead of sending you an email |  | 2015-09-03 | fixed
34 | in ScreenShot folder | It is a folder that has all the pictures needed for the front end of products |  | 2015-09-03 | fixed | It is call : SR34-Picture for all products
35 | Recycle | Replace the text to the one i provided |  |  | fixed
106 | Migrate to my Server |  | Desktop and mobile | 2015-08-27 | fixed | Mean to put everything on : Stopoint.com
128 | Expiry Date is hardcoded in the PDF | Expiry date should be order date + 30 days. | Desktop and mobile | 2015-09-03 | fixed | You have until 2015-08-04 to ship your device.
129 | Generate Label in MyOrder should open new tab/window | Generate label needs to open new tab/window | Desktop and mobile | 2015-09-03 | fixed
46 | Recycling | add recycling page | Desktop and mobile | 2015-08-21 | fixed | Yes put link in the bottom too | Wehave displayed it for product have amount zero, Do you want same recycle link in bottom too